## Topics & Agenda Items
Topic List / Agenda Development
Program Learning Objectives:
| · Program objectives: | In attending this Industry Day program, Participants will:
1 | o Engage in getting to know each other and their technologies
2 | o Understand CSNE research efforts
3 | o Engage in networking with faculty and students as well as each other
4 | o Participate in workshops: get tech transfer ideas, project collabs, and inter-member collabs
5 | [8 empty] | Consider referral building??
Day/Night Prior |  |  |  | Objective Met | Duration | Time | Owner
| AV/Sound Check |  |  |  | TBD | TBD | Darin?
| Faculty Rehearsal Mtg |  | (Dinner? Lunch?) |  | 90min | TBD | SR | Walk through agenda, day,
| Final Slide Review w/ Faculty |  |  |  | 60min | TBD
Evening |  |  |  |  | Duration | Time | Owner |  | Location (West) |  |  | Location (East)
[5 empty] | 60min | 5:00pm | FES | [5 empty] | Leverage content developed for Baylor Fellows Program
[5 empty] | 90min | 6:00pm
| Cocktail Reception |  |  | networking | 90min | 7:30pm | HH/DL
Industry Day
Sunday, April 10, 2016
Arrivals during Day
| 6:00 - 8:30pm | Dinner Event: Industry & Student Dinner |  |  |  | Walker Ames (Kane Hall)
Reception & Drinks from 6:-6:30pm; shuttle return to Watertown hotel 8:30
Monday, April 11, 2016
| 8:00am | Shuttle Departs Watertown for CSNE |  |  |  |  | Watertown Seattle
| 8:15 |  | Arrival at CSNE, Breakfast | [5 empty] | CSNE Headquarters
| 8:30 |  | Introduction | [7 empty] | Scott Ransom, CSNE ILO
| 8:35 |  | CSNE Strategic Vision | [6 empty] | Rajesh Rao, CSNE Director
| 8:50 |  | CSNE Industry Strategic Vision | [5 empty] | Scott Ransom
| 9:00 |  | Industry Round Robin | [6 empty] | Industry Members
| 10:30 |  | Break
| 11:00 |  | Research Overview | [6 empty] | CSNE Faculty
|  |  |  | Neural Interface and Recording |  |  | Visvesh Sathe, Sam Kassegne
| Circuits and Closed-Loop Stimulation |  | Chris Rudell
|  |  |  | Implanted Computation |  |  |  | Eric Shea-Brown
| Wireless System Design |  |  |  | Matt Reynolds
|  |  |  | Neuroethics |  |  |  |  | Eran Klein
| 12:00 |  | Lunch | [8 empty] | Suite 201
| 12:45 |  | Student Poster Session | [6 empty] | CSNE Students
| 1:30 |  | Tech Transfer – Making the most of IP |  |  | Deborah Alterman, Tech Manager, CoMotion
| 2:15 |  | Workshops (Choose 1 of these 4 Options)
|  |  |  | Leveraging SBIRs and SECOs |  | Jared Olson and Sandy Heck |  | Suite 201
|  |  |  | Licensing Technology |  |  | Deborah Alterman |  |  | Conf Room
|  |  |  | Student / Industry Q&A and Internship Discussion |  |  |  | Main Room
|  |  |  | Project Meetings |  |  | Pre-scheduled |  |  |  | Offices & Labs
| 3:15 |  | Break
| 3:30 |  | CSNE Sustainability (post NSF Graduation) Discussion |  |  | All
| 4:00 |  | Private Session: NSF Site Visit Briefing |  |  |  |  | Tim Denison
| 4:45 |  | Wrap Up, Q&A | [7 empty] | All
| 5:15 |  | Adjourn, Shuttle Departs for Watertown Seattle
| 6:30 – 8:30 | Open Dinner | [7 empty] | Restaurant List provided

## Placemats
Placemats for Industry Day
Item | Contents | Owner | Notes
Mug |  | Scott
Pad of Paper |  | Josh
Pen |  | Josh
Post-it Notes |  | Scott
Name Tent |  | Deb
CSNE Folder |  | Scott
| IP Report | Scott
| Annual Report Industry Section | Deb
| Updated Industry Brochure | Wayne
| Post-Event Survey | Scott

## Industry Day Task List
Industry Day Planning Checklist | [5 empty] | T-Minus
Bay Laurel Catering 206-685-2051 | Status | week after | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | Week 11 | Week 12 | Owner (s) | Owner | Notes
Meeting Design & Communication
Finalize Industry Day Date / NSF Site Visit | Done | [14 empty] | Raj / Eric | May 1st Industry Day, May 2nd NSF Site Visit | bar: T-Minus Week 12
Call with core IAB members - topics list | Done | [14 empty] | Scott | bar: T-Minus Week 11
Create Topics list | Done | [14 empty] | Scott | bar: T-Minus Week 11
Share with CSNE Leadership | Done | [14 empty] | Scott | bar: T-Minus Week 11
Create Agenda Draft | Done | [14 empty] | Scott | bar: T-Minus week 10
Send Save-the-Date email to IAB | Done | [14 empty] | Scott | bar: T-Minus Week 12
Create IAB Attendance Roster | Done | [14 empty] | Scott | Just 2 people yet to confirm | bar: week 3
Send instructions for attendees on hotel / air | Done | [14 empty] | Scott | bar: T-Minus week 5
Inform Faculty & Students | Done | [14 empty] | Raj / Eric | bar: T-Minus week 9
Create CSNE Roster | Done | [14 empty] | Deb | Deb is collecting MIT and SDSU attendees | bar: week 3
Create xls w Name Badge / Tent list | Done | [14 empty] | Deb | will populate with Deb's attendee list plus Industry RSVPs | bar: week 2
Planning Meeting with Staff | Done | [14 empty] | Scott | bar: T-Minus week 5
Review / Oritentation with all Faculty | Done | [14 empty] | Scott | bar: week 1
Create "New Member" welcome announcement / email | Done | [14 empty] | Wayne | Posted on website | bar: week 2
SWOT Analysis
Check core availability | Done | [14 empty] | Scott | bar: T-Minus week 5
Send SWOT from Last year | Done | [14 empty] | Scott | bar: T-Minus week 5
Schedule Conf Call with IAB members | Done | [14 empty] | Scott | bar: T-Minus week 4
Host SWOT Conf Call | Done | [14 empty] | Scott | EQuIP Call March 30, 2017 | bar: week 3
Create initial draft for Heather and IAB | Done | [14 empty] | Scott | bar: week 3
Write up Results | Done | [14 empty] | Scott | Sent to IAB | bar: week 2
Share Internally | Done | [14 empty] | Scott | bar: week 2
email Results to Heather and IAB | Done | [14 empty] | Scott | bar: week 1
Write Response | Done | [14 empty] | leadership | bar: week 1
Share response with IAB | Done | [14 empty] | Scott | bar: week 1
Upload to Sharepoint | Done | [14 empty] | Deb | Scott to send it to Deb when complete | bar: week 1
Agenda, Topics and Speakers
Identify all Speakers | Done | [14 empty] | Scott | Holding until Mock Site Visit day | 10 min Neural Recording & Electrodes – Visvesh Sathe | bar: T-Minus week 5
Connect with Speakers: | [17 empty] | Overview, including who’s the team
Ruth SBIR / SECO | Done | [14 empty] | Scott | Conf Call code | Key Areas of Focus | bar: T-Minus week 4
Lisa Norton - Tech Transfer | Done | [14 empty] | Scott | She'll bring Ryan too | Barriers | bar: T-Minus week 4
10 min Neural Recording & Electrodes – Visvesh Sathe | Done | [14 empty] | Scott | Chet and Raj deciding on these speakers | How we are Tackling those Barriers (testbeds, projects?) | bar: week 2
10min Hi V stim w/ Low V CMOS – Chris Rudell | Done | [14 empty] | Scott | they'd like to wait until after the mock day to select these | Advertise any Related Posters | bar: week 2
10min Wireless Power & Wireless Communication – Matt Reynolds | Done | [14 empty] | Scott | bar: week 2
10min Computational Neuro – Eric Shea-Brown | Done | bar: week 2
5min Neuroethics Overview – Eran Klein | Done | bar: week 2
CSNE Strategic Vision - Rajesh Rao | Done | [14 empty] | Scott |  | 10min Hi V stim w/ Low V CMOS: Single Chip discussion – Chris Ruddell | bar: T-Minus week 4
Scott create Industry Slides and Intro | Done | [14 empty] | Scott | Include the "optimal centers are like…." chart | Overview, including who’s the team | bar: week 2
Create outline for the Faculty talks for Industry | Done | [14 empty] | Scott | Chet and Raj to approve, then send to speakers / owners | Key Areas of Focus | bar: week 1
Send email to Industry w who is in what group | Done | [14 empty] | Scott | Also include final agenda and breakout workshops | How we are Tackling those Barriers (testbeds, projects?) | bar: week 1
Finalized talk titles | Done | [14 empty] | Scott |  | Advertise any Related Posters | bar: week 3
Pull pics and videos off drop box | Done | [14 empty] | Scott
Send Draft Agenda to IAB | Done | [14 empty] | Scott |  | 10min Wireless Power & Wireless Communication – Matt Reynolds | bar: T-Minus week 4
Finalize Agenda | Done | [14 empty] | Scott | Good draft sent last week to IAB | Overview, including who’s the team | bar: week 2
Send Final Agenda to all attendees | Done | [14 empty] | Scott | Once attendee is finalized | Key Areas of Focus | bar: week 2
Create Program Evaluation Form | Done | [14 empty] | Scott |  | Barriers | bar: week 3
Send students information on Posters and breakouts | Done | [14 empty] | Scott | made this a general breakout | How we are Tackling those Barriers (testbeds?) | bar: week 2
Registration | [17 empty] | Advertise any Related Posters
Collect Registrations from IAB (email) | Done | [14 empty] | Scott | bar: T-Minus week 4
Collect Registrations from MIT Attendees | Done | [14 empty] | Deb |  | 10min Implanted Computation – Eric Shea-Brown | bar: T-Minus week 4
Collect Registrations from UW Attendees | Done | [14 empty] | Deb |  | Overview, including who’s the team | bar: T-Minus week 4
Collect Registrations from SDSU Attendees | Done | [14 empty] | Deb |  | Key Areas of Focus | bar: T-Minus week 4
Send instructions for IAB on reserving hotel | Done | [14 empty] | Scott |  | Barriers | bar: T-Minus week 4
IAB Registration Confirmations | Done | [14 empty] | Scott |  | How we are Tackling those Barriers (testbeds?) | bar: week 3
Confirm Hotel Reservations | Done | [14 empty] | IAB | IAB will do hotels on their own | Advertise any Related Posters | bar: week 2 to T-Minus week 4
Confirm Flights Arranged | Done | [14 empty] | Josie | Only for out-of-state start-ups | bar: week 2 to T-Minus week 4
Send email Confirmation to IAB attendees | Done | [14 empty] | Scott | Remind about parking, the restaurants, dietary restrictions | 5min Neuroethics Overview – Eran Klein | bar: week 1
Select CSNE Attendee list (Max Cap = 60 ) | Done | [14 empty] | Scott | 25 IAB, XX Faculty, XX Students, Raj, Chet, Joel, Sam | Key areas of focus | bar: week 3
Send email Confirmation to CSNE Attendees | Done | [14 empty] | Eric |  | Why this is important | bar: week 1
Flight Reminder | Done | [14 empty] | Scott |  | Quick summary of efforts (embedded in labs, patient interviews) | bar: week 2
Hotel/Food/Logistics
Send Attendee flight list to Jose | Done | [14 empty] | Scott | bar: week 3
Select Restaurant for Sunday Reception | Done | [14 empty] | Scott | Walker Ames Room | bar: week 3
Reserve Restaurant - Sunday Dinner | Done | [14 empty] | Josh | Deb Reserved Walker Ames room already | bar: week 2
Create map: between Marriott and Walker Ames | Done | [14 empty] | Deb | it's a straight shot but a map is nice
A/V Needs established | Done | [14 empty] | Scott | bar: T-Minus week 5
Test AV system with extended screen | Done | [14 empty] | Josh / Eric | bar: week 3
Test Polycom w/ GoTo Meeting on presentation laptop | [15 empty] | Josh | bar: week 3
Communicate to Students on Posters, send Template | Done | [14 empty] | Eric | bar: T-Minus week 9
Create Food and Snack List | Done | [14 empty] | Josh | based on attendee list, Scott to help | bar: week 3
Choose menu for Sunday Dinner | Done | [14 empty] | Scott / Team | Deb provided catering menu to Scott | bar: week 2
Order Food for Monday: Bkfst, Lunch | Done | [14 empty] | Josh | Food = breakfast, lunch, dessert, sodas. (coffee and afternoon snacks pulled from CSNE cupboard) | bar: week 3
Get Sandwich Board for Sidewalk | Done | [14 empty] | Josh | Check with Unico for board requirements / if ok to stand | bar: week 3
Provide Attendee count to Josh for meals | Done | [14 empty] | Scott | bar: week 3
Seating chart for NSF lunch / industry seating | Done | [14 empty] | Scott | Send to Raj for approval | bar: week 3
Cookies & Sodas for Afternoon Break | Done | [14 empty] | Deb | These will be pulled from CSNE Cupboard | bar: week 3
Create Table Placemat:
Print IP Report | Done | [14 empty] | Scott | bar: week 2
Name Tent | Done | [14 empty] | Nikki | bar: week 2
Update Industry Brochure with Logos | Done | [14 empty] | Wayne | He'll print about 40, SR will take extras to Boston | bar: week 2
Print Annual Report Industry Section w/ Industry Cover | Done | [14 empty] | Deb | bar: week 2
WiFi instructions | Done | [14 empty] | Josh | bar: week 2
Attendee List and Welcome Letter | Done | [14 empty] | Scott | bar: week 2
Evaluation Form | Done | [14 empty] | Scott | bar: week 2
Pad paper, Pen | Done | [14 empty] | Scott | bar: week 1
CSNE Jump Drive and Squishy Brain | Done | [14 empty] | Scott | bar: week 1
Stuff Folders with the Placemat Materials | Done | [14 empty] | Noah | bar: week 1
Name Badges | Done | [14 empty] | Nikki | For all attendees, back includes where they are for lunch | bar: week 2
Take Photos of Event | Done | [14 empty] | Eric | Day of event | bar: week 1
Get some Roof Access Cards for breaks | Done | [14 empty] | Josh | bar: week 2
Tables and Chairs rented for Suite 201 | n/a | [14 empty] | n/a | ABC Rentals - 40 max in the room | bar: T-Minus week 4
Get extra mics | Done | [14 empty] | Josh | bar: week 2
Start Writing Director's Cut | Done | [14 empty] | Scott | bar: week 3
Presentations / Posters / Demos
Confirm Faculty | Done | [14 empty] | Scott | Waiting til Mock per Raj / Chet | bar: T-Minus week 4
Confirm Posters w/ Students | Done | [14 empty] | Eric | Posters get printed 1 week prior | bar: week 2
Track Poster Completion | Done | [14 empty] | n/a | Students | bar: week 1
Collect Slides from IAB Members | Done | [14 empty] | Scott | Will probably get those at the dinner Sunday night | bar: week 1
Compile Single Member Presentation | Done | [14 empty] | Scott | bar: week 1
Collect Slides from Faculty Presenters | Done | [14 empty] | Scott | bar: week 1
Compile Single Faculty Presentation | Done | [14 empty] | Scott | bar: week 1
Track Demo Stations Needed | Done | [14 empty] | Scott | So far just Cactus wants a demo station (Green Cabinet Area) | bar: week 3
Order Skirts for 2 Demo Tables | n/a | [14 empty] | Deb | bar: week 3
Get Demo Tables | n/a | [14 empty] | Scott | Decided to use the Green Cabinet wooden table | bar: week 3
Table Covers for Demo Tables? | n/a | [14 empty] | Deb | bar: week 3
Reserve rooms/spaces on the CSNE Calendar | Done | [14 empty] | Eric | bar: T-Minus Week 12
Print Industry Banner | Done | [14 empty] | Wayne | Include logos from all current IAB members | bar: week 2
Print Posters | Done | [14 empty] | Deb | by 3/31 posters done, print April 4 | bar: week 2
Print Giant Agenda | Done | [14 empty] | Deb | Send agenda to Deb | bar: week 2
Assign Time Keeping | Done | [14 empty] | Scott | SLC student can do it? | bar: week 2
Update the IP Report with Polina's IP | n/a | [14 empty] | Scott | bar: week 3
Day Before Meeting
Test Projector / AV set up | Done | [14 empty] | Josh | bar: week 1
Set up Classroom Tables & Chairs | Done | [14 empty] | Scott | bar: week 1
Set up Posters | Done | [14 empty] | Students | bar: week 1
Clean Galley | Done | [14 empty] | Scott | bar: week 1
Set up Demo Tables | Done | [14 empty] | Scott | bar: week 1
Set Demos on Tables? | n/a | [14 empty] | IAB | bar: week 1
Hang Industry Banner | Done | [14 empty] | Deb | bar: week 1
Clip Skirts to Tables | n/a | [14 empty] | Deb | bar: week 1
Get time keeping device | Done | [14 empty] | Scott | bar: week 1
Set up easel and newsprint | n/a | [14 empty] | Deb | 4 or 5 easels in poster area - for each restaurant | bar: week 1
set out pads, folders, post-its and pens | [15 empty] | Scott | in folders | bar: week 1
Day of Meeting
Set up Newsprint Easel, Dinner options | n/a | [14 empty] | Scott | bar: week 1
Set out placemats for industry members | Done | [14 empty] | Scott | bar: week 1
set up registration table w/ badges and name tents | Done | [14 empty] | Josh | bar: week 1
Set up Laptop | Done | [14 empty] | Scott | Password is csne1414 | bar: week 1
Make sure signage / entry screen working | Done | [14 empty] | Josh | bar: week 1
Collect Surveys | Done | [14 empty] | Scott | bar: week 1
Post Meeting Evaluation Plan
Outline how we will be following up on attendees | Done | [14 empty] | Scott | swot debrief, slides upon request; consider website tab | bar: T-Minus week 5
Presentations/Hand outs/USB/weblink | [15 empty] | Scott | Can we do this? | bar: week 3
Capture content for attendees that are unable to attend | Done | X | [13 empty] | Scott | consider slides on CSNE website industry tab
Create Google Docs for Posters | Done | X | [13 empty] | Scott | So IAB can view posters again after mtg
Plan Follow-up Calls for Absent Industry Members | Done | X | [13 empty] | Scott
Send thank-you email to IAB and incl. NSF q's | Done | X | [13 empty] | Scott | on Raj's behalf
Send thank-you email to Speakers | Done | X | [13 empty] | Scott
Buy & Distribute Starbuck's thank-you cards |  | X | [13 empty] | Scott | Can we do this?
Review Surveys | Done | X | [13 empty] | Scott
Report Results to leadership team | Done | X | [13 empty] | Scott | two weeks post event

## Attendees Flights Hotel
count | Company | Name | RSVP? | Student Dinner | Industry Day | MonDin | NSF Mtg | Wed | Table# | Breakout | Hotel? | Arrival Date | Notes
1 | Advanced Brain Monitoring | Chris Burka on phone | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
1 | ArianRF | Nader Kalantari | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 | Mon by 11am | CSNE pay for flight
1 | ARM | Andrew Sloss | 1 | 1 | 1 | 1 | 1 | 1 | 10 |  | 0
0 | ARM | Karthik Ranjan | 1 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0
0 | ARM | Mbou Eyole | 1 | 1 | 1 | 1 | 1 | 0 | 6 |  | 0
0 | ARM | Joseph Fernando | 1 | 1 | 1 | 1 | 1 | 1 | 6 |  | 0
0 | Blackrock Microsystems | Kian Toreb | 1 | 0 | 0 |  | 0 |  | 0 |  | 0
1 | Blackrock Microsystems | Nick Halper | 1 | 0 | 1 |  | 1 |  | 9 |  | 1
1 | Cactus Semiconductor | Andy Kelley | 1 | 0 | 1 |  | 0 |  | 0 |  | 1
1 | Cadence Neuroscience | Kent Leyde | 1 | 0 | 1 |  | 1 |  | 13 |  | 0
0 | Cadence Neuroscience | Doug Sheffield | 1 | 0 | 0 |  | 1 |  | 13 |  | 0
0 | Cambridge NeuroTech | Tahl Holtzman | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0 | Cerevast Medical | John Alleman | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
1 | Cirtec | Heather Dunn | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 |  | CSNE pay for flight, hotel, ground
0 | Ekso Bionics | Kurt Amundson | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
1 | Ekso Bionics | Matt Cuellar | 1 | 1 | 1 |  | 0 |  | 0 |  | 0
1 | Embotic Technology | Joseph Xu | 1 | 0 | 1 |  | 1 |  | 9 |  | 0
0 | Epoch Medical | Michael Ballas | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0 | Galvani Bioelectronics | Roy Katso | 0 |  |  |  | 0 |  | 5 |  | 0
0 | Intel | Asli Arslan | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
1 | Intel | Nese Alyuz Civitci | 1 | 0 | 1 |  | 0 |  | 0 |  | 1
0 | Kernel | Bryan Johnson | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0 | Kernel | Jacob Bernstein | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0 | LeafLabs | Justin Kinney | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0 | LeafLabs | Chris Chronopolous | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0 | LeafLabs | Bill Dixon | 0 | 0 | 0 |  | 0 |  | 3 |  | 0
0 | LivaNova | Jason Begnaud |  | 0 | 0 |  | 0 |  | 11 |  | 0
0 | LivaNova | Maryam Ravan |  | 0 | 0 |  | 0 |  |  |  | 0
1 | Medtronic | Tim Denison on phone | 1 | 1 | 0 |  | 1 |  | 1 |  | 0
0 | Medtronic | Chris Pulliam | 1 | 0 | 1 |  | 1 |  | 11 |  | 1
1 | Microsoft | Joseph Sirosh | 1 | 0 | 0 |  | 1 |  | 6 |  | 0
0 | Microsoft | Anand Raman | 1 | 0 | 0 |  | 1 |  | 10 |  | 0
0 | Microsoft | Wee Hyong Tok | 0 | 0 | 0 |  | 0
0 | Microsoft | Miah Wander | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
1 | MultiModal Health | Brian Mogen | 1 | 0 | 1 |  | 0 |  |  |  | 0
0 | MulitModal Health | Tyler Libey | 0 | 0 | 0 |  | 0 |  |  |  | 0
1 | NeuroRecovery Technologies | Nick Terrafranca | 1 | 1 | 1 |  | 0 |  | 5 |  | 1
1 | Neurotech | Kristine Wildner | 1 | 1 | 1 |  | 0 |  | 0 |  | 0
0 | Neurotech | Sedalia Cole, R. EEG T. | 1 | 0 | 1 |  | 0 |  | 0 |  | 0
0 | OpenBCI | Conor Russomanno | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
0 | OpenBCI | Joel Murphy | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
1 | Pramak | Mak Agashe | 1 | 0 | 1 |  | 1 |  | 7 |  | 0
0 | Reach Bionics | Sandy Heck | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
1 | Ripple | Andrew Wilder | 1 | 1 | 1 |  | 1 |  |  |  | 1
0 | Ripple | Jessi Mischel | 1 | 1 | 1 |  | 1 |  |  |  | 1
1 | Washington Research Found | Beth Etscheid | 1 | 0 | 0 |  | 1 |  |  |  | 0
0 | Washington Research Found | Kim Emmons | 1 | 0 | 1 |  | 0 |  | 0 |  | 0 | late M AM
0 | WhiteMatter | Tim Blanche | 0 | 0 | 1 |  | 0 |  | 0 |  | 0
1 | WhiteMatter | Tyler Maxfield | 1 | 0 | 1 |  | 0 |  | 8 |  | 0
1 | WiBotic | Ben Waters | 1 | 0 | 0 |  | 1 |  |  |  | 0
0 | WiBotic | Josh Smith | 1 | 0 | 0 |  | 1 |  |  |  | 0
20 | TOTAL |  | 30 | 11 | 23 |  | 19 |  |  |  | 9
[9 empty] | Hyong Chan |  | 1
[9 empty] | Richard Anderson |  | 1
[9 empty] | Scott Ransom |  | 1
12
| Student | Name | poster
1 |  | Mark Wronkiewicz | 0
1 |  | Katie Ly | 0
1 |  | Juhi Farooqui | 0
1 |  | Andrew Haddock | 1
1 |  | Brady Houston | 1
1 |  | Apoorva Sharma | 1
1 |  | David Bjanes | 1
1 |  | Maggie Thompson | 1
1 |  | Katherine Pratt | 1
1 |  | Jeneva Cronin | 1
1 |  | Fatma Inanici | 1
1 |  | Dev Sarma | 1
1 |  | David Caldwell | 1
1 |  | James Wu | 1
1 |  | John Uehlin | 1
1 |  | Nile Wilson | 1
Presenters
1 |  | Raj Rao
1 |  | Chet Moritz
1 |  | Eric Shea-Brown
1 |  | Eran Klein
1 |  | Matt Reynolds
1 |  | Chris Rudell
1 |  | Visvesh Sathe
0 |  | Sam Kassegne
1 |  | Scott Ransom
Staff attending
1 |  | Eric Chudler
1 |  | Deb Harper
1 |  | Wayne Gillam
1 |  | Josh Patrick
28 | Total non-IAB attendees
| 51 | Total Attendees Monday

## Meal Sheet
Meal Attendees
Sunday | Industry / Student Dinner |  | Count | Industry Count | Student Count | Other
Industry
|  | John Alleman | 1 | 1
|  | Brad Zakes | 1 | 1
|  | Mark Moehring | 1 | 1
|  | Andy Kelly | 1 | 1
|  | Andrew Meyer | 1 | 1
|  | Anand | 1 | 1
|  | Heather Dunn | 1 | 1
|  | Tim Denison | 1 | 1
|  | 1 | 1
|  | 1 | 1
|  | 1 | 1
|  | 1 | 1
|  | 1 | 1
|  | Michael Ballas | 1 | 1
|  | Anthony LaMarca | 0 | 0
|  | Nick Terrafranca | 1 | 1
|  | Brian Mogen | 1 | 1
|  | Tyler Libey | 1 | 1
|  | Lars Crawford | 1 | 1
|  | Beth E | 0 | 0
|  | Nick Terrafranca | 1 | 1
|  | Conor | 1 | 1
|  | Karthik Ranjan | 1 | 1
Students
|  | Nile Wison | 1 |  | 1
|  | James Wu | 1 |  | 1
|  | Katherine Pratt | 1 |  | 1
|  | Akshay Chalana | 1 |  | 1
|  | Andrew Haddock | 1 |  | 1
|  | David Caldwell | 1 |  | 1
|  | Jeffrey Herron | 1 |  | 1
Other / CSNE
|  | Scott Ransom | 1 |  |  | 1
|  | Wayne Gillam | 0 |  |  | 1
|  | Josh Patrick | 0 |  |  | 1
|  | Rad Roberts | 1 |  |  | 1
|  | Raj Rao | 1
|  | Chet | 1
|  | Eric | 1
|  | Joel | 1
|  | Sam | 1
|  | Tyler Dean Maxfield | 1
|  | Tim Blanche | 1
Sunday | Industry / Student Dinner |  | 37 | 16 | 7 | 4
|  |  | Tot | Ind | Stu | Other

## Badge and Tent list
Name Badge and Tent List
c | Name | Company | Tent? | Monday's Lunch Location | S201 Count | Other Count
1 | Timothy Denison | Medtronic | Y | Suite 201 | 1
1 | Shivkumar Sabesan | LivaNova | Y | Suite 201 | 1
1 | Heather Dunn | Cirtec | Y | Suite 201 | 1
1 | Kurt Amundson | Ekso Bionics | Y | Suite 201 | 1
1 | Kian Torab | Blackrock Microsystems | Y | Suite 201 | 1
1 | Chris Berka | Advanced Brain Monitoring | Y | Suite 201 | 1
1 | Stephanie Korszen | Advanced Brain Monitoring | Y | Suite 201 | 1
1 | Michael Ballas | Epoch Medical | Y | Suite 201 | 1
1 | Sandy Heck | Reach Bionics | Y | Suite 201 | 1
1 | Anthony LaMarca | Intel | Y | Suite 201 | 1
0 | Beth Etscheid | Washington Research Foundation | Y | Suite 201 | 0
1 | John Alleman | Cerevast Medical | Y | Suite 201 | 1
1 | Andy Kelly | Cactus Semiconductor | Y | Suite 201 | 1
1 | Karthik Ranjan | ARM | Y | Suite 201 | 1
1 | Anand Raman | Microsoft | Y | Suite 201 | 1
1 | Brian Mogen | MultiModal Health | Y | Suite 201 | 1
1 | Tyler Libey | MultiModal Health | Y | Suite 201 | 1
1 | Lars Crawford | MultiModal Health | Y | Suite 201 | 1
1 | Andrew Meyer | LeafLabs | Y | Suite 201 | 1
1 | Conor Russomanno | OpenBCI | Y | Suite 201 | 1
1 | Nick Terrafranca | NeuroRecovery Technologies | Y | Suite 201 | 1
STAFF
1 | Rajesh Rao | Director, CSNE | N | Suite 201 | 1
1 | Chet Moritz | Deputy Director, CSNE (UW) | N | Suite 201 | 1
1 | Joel Voldman | Deputy Director, CSNE (MIT) | N | Suite 201 | 1
1 | Sam Kassegne | Deputy Director, CSNE (SDSU) | N | Suite 201 | 1
1 | Eric Chudler | Education Director, CSNE (UW) | N | Suite 201 | 1
1 | Wayne Gillam | Marketing Manager, CSNE (UW) | N | CSNE |  | 1
1 | Deborah Harper | Administrative Director, CSNE (UW) | N | CSNE |  | 1
1 | Scott Ransom | Industrial Liaison Officer, CSNE (UW) | N | Suite 201 | 1
Thrust & Testbed Leaders
1 | Josh Smith | UW | N |  | 1
1 | Adrienne Fairhall | UW | N |  | 1
1 | Eric Shea-Brown | UW | N |  | 1
1 | Sara Goering | UW | N |  | 1
1 | Howard Chizeck | UW | N |  | 1
1 | Steve Perlmutter | UW | N |  | 1
1 | Polina Anikeeva | UW | N |  | 1
1 | Jeffrey Ojemann | UW | N |  | 1
Students
1 | James Wu | UW | N |  |  | 1
1 | Katherine Pratt | UW | N |  |  | 1
1 | Jeffrey Herron | UW | N |  |  | 1
1 | Akshay Chalana | UW | N |  |  | 1 | what does she do? She's on csne list but no research?
1 | Andrew Haddock | UW | N |  |  | 1
1 | David Caldwell | UW | N |  |  | 1
1 | Jenny Cronin | UW | N |  |  | 1
1 | Greg Moore | UW | N |  |  | 1
1 | Tim Brown | UW | N |  |  | 1
1 | Boying Meng | UW | N |  |  | 1
1 | Nile Wilson | UW | N |  |  | 1
1 | Matt Elzinga | UW | N |  |  | 1
1 | Dev Sarma | UW | N |  |  | 1
1 | Melissa Smith | UW | N |  |  | 1
1 | Matthew D'Asaro | MIT | N |  |  | 1
1 | Stephanie Chen | MIT | N |  |  | 1
1 | David Bjanes | UW | N |  |  | 1
1 | Margaret Thompson | UW | N |  |  | 1
1 | Brody Mahoney | UW | N
Other Faculty Researchers
1 | Jeff Lang | MIT | N |  |  | 1
1 | Ashkan Ashrafi | SDSU | N |  |  | 1
1 | Jacques Rudell | UW | N |  |  | 1
1 | Mahasweta Sarkar | SDSU | N |  |  | 1
1 | Vladamir Bulovic | MIT | N |  |  | 1
1 | Les Atlas | UW | N |  |  | 1
1 | William Shain | UW | N |  |  | 1
1 | Amir Alimohammad | SDSU | N |  |  | 1
1 | Visvesh Sathe | UW | N |  |  | 1
1 | Santosh Nagaraj | SDSU | N |  |  | 1
1 | Yusuf Ozturk | SDSU | N |  |  | 1
1 | Karen Kay-Newman | SDSU | N |  |  | 1
1 | Felix Darvas | UW | N |  |  | 1
1 | Kristi Morgansen | UW | N |  |  | 1
1 | Thomas Grabowski | UW | N |  |  | 1
1 | Eb Fetz | UW | N |  |  | 1
1 | Mehrdad Jazayeri | MIT | N |  |  | 1
1 | Katherine Steele | UW | N |  |  | 1
1 | Michael Rudd | UW | N |  |  | 1
1 | Tom Daniel | UW | N |  |  | 1
1 | Russ Tedrake | MIT | N |  |  | 1
1 | Brian Hafner | UW | N |  |  | 1
1 | Glenn Klute | UW | N |  |  | 1
1 | Emo Todorov | UW | N |  |  | 1
1 | Blake Hannaford | UW | N |  |  | 1
1 | Ke Huang | SDSU | N |  |  | 1
1 | Jared Olson | UW | N |  | 1
1 | Pierre Mourad | UW | N |  | 1
Other Partners
1 | Deborah Alterman | CoMotion | N |  | 1
1 | Ryan Buckmaster | CoMotion | N |  | 1
1 | Linda | CoMotion | N |  | 1
1 |  | SAB Representative?? |  |  |  | 1
87 | TOTAL ATTENDEES |  |  | S201 Count: | 39 | 47 | CSNE classroom lunch count
Breakfast: 60
Lunch: 40 Boxed Wraps for Rm201, 35 Jimmy Johns for galley area

## Evaluation Data
April 2016 (Year 5) Industry Day Evaluation Results
|  |  |  | Responses from: IAB | 11
|  |  |  | Faculty | 1
|  |  |  | Students | 6
|  |  |  | Staff | 0
1 = not relevant, 5 = very valuable
IAB | Fac | Stu | Stf | Most Valuable | Least Valuable | Improvements | Student Dinner | Strat Overview | Ind Round Robin | Research Overview | Poster Session | Tech Transfer | Workshops | Sustainability
1 |  |  |  | Great diversity of industry partners, awesomely potent group. Sustainability discussion was intriguing. | More representation from other academic members | Members should get slides to you sooner | 5 | 5 | 4 | 4 | 4 | 3 | 5 | 5
1 |  |  |  | Industry Round Robin |  |  | 4 | 4 | 5 | 5 |  |  | 4 | 4
1 | [6 empty] | 5 | 5 | 4 | 5 | 5 | 4 | 3 | 5
1 | [6 empty] | 3 | 4 | 4 | 5 | 4 | 3 | 5 | 4
1 |  |  |  | Round Robin and the Poster Session |  |  | 5 | 4 | 5 | 4 | 4 | 5 | 3 | 4
1 |  |  |  | Round Robin and Research Update |  | well run day, organized and purposeful | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 5
1 |  |  |  | Research Overview | Tech Transfer session too long | Include the other schools or elimnate | 5 | 4 | 4 | 5 | 4 | 3 | 4 | 5
1 |  |  |  | diverse csne research and connect w/ other participants |  | raj chet joel sam not at dinner | 3 | 4 | 5 | 5 | 5 | 3
1 |  |  |  | Research Overview | workshops werent relevant |  |  | 5 | 5 | 5 | 4 | 4 | 3 | 4
1 |  |  |  | round robin and workshops | where was MIT and SDSU faculty? |  |  | 4 | 5 | 5 | 5 | 4 | 5 | 4 | IAB Only Numbers:
1 |  |  |  | round robin and research |  | don’t exclude MIT/SD, they should be there | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 4 | 4.25 | 4.4 | 4.6 | 4.8 | 4.4444 | 3.6667 | 4.1111 | 4.4444
| 1 |  |  | Round Robin |  | really very good day |  | 4 | 5 | 5 | 5 | 4 | 5 | 5
|  | 1 |  | Student Dinner, Round Robin |  | Best Industry Day ever! | 5 | 4 | 5 | 3 | 5 | 3 | 4 | 5
|  | 1 |  | round robin and conversations during posters |  | pick a better poster printer, posters printed poorly |  | 5 | 5 | 5 | 4 |  |  | 5
|  | 1 |  | opportunity to network with the industry partners, formed new connections and may have sparked interest in hackathon sponsorship. Also got very useful career advice throught the informal panel |  |  |  |  | 5 | 3 | 3 | 2 | 5 | 5
|  | 1 |  | student/industry breakout workshop and sustainability discussion |  | tech transfer was good topic but the talk wasn't in-depth enough |  |  | 5 | 4 | 3 | 1 | 5 | 4
|  | 1 |  | hearing from the industry members and getting career advice | IP discussion | get faculty to the student dinner | 3 |  | 5 |  | 3 | 3 | 4 | 4
|  | 1 |  | career advice for students in workshop | strategic vision since I'm already familiar with csne | increased time for 1:1 interactions w IAB members |  | 5 | 5 | 5 | 4 | 5 | 5 | 4
11 | 1 | 6 | 0 | COUNT |  | Average Scores: | 4.2727 | 4.4667 | 4.7778 | 4.5882 | 4.2353 | 3.375 | 4.375 | 4.4706

## Evaluation Results
Evaluation Results
|  | All | IAB Only
| Topic | Avg Score |  | Most Valuable (Raw Data) | Valuable Themes | count
| Round Robin | 4.8 | 4.6 | Research Overview | Research Overview | 5
| Research Overview | 4.6 | 4.8 | diverse csne research and connect w/ other participants | Round Robin | 9
| Strategic Overview | 4.5 | 4.4 | Research Overview | Networking | 3
| Sustainability | 4.5 | 4.4 | round robin and workshops | Workshops | 2
| Workshop | 4.4 | 4.1 | round robin and research | Student Dinner | 1
| Student Dinner | 4.3 | 4.3 | Round Robin | Posters | 2
| Poster Session | 4.2 | 4.4 | Student Dinner, Round Robin | Sustainability | 2
| Tech Transfer | 3.4 | 3.7 | round robin and conversations during posters | Career Advice IAB | 2
|  |  |  | opportunity to network with the industry partners, formed new connections and may have sparked interest in hackathon sponsorship. Also got very useful career advice throught the informal panel | IAB is Awesome | 1
|  |  |  | student/industry breakout workshop and sustainability discussion | Plan / Execution | 4
hearing from the industry members and getting career advice
career advice for students in workshop
Great diversity of industry partners, awesomely potent group. Sustainability discussion was intriguing.
Industry Round Robin
Round Robin and the Poster Session
Round Robin and Research Update
Well Planned or Seamless Execution
|  |  |  | Least Valuable (Raw Data) | Least Val Themes | count
|  |  |  | More representation from other academic members | MIT / SDSU missing | 4
|  |  |  | Tech Transfer session too long | Tech Transfer | 2
|  |  |  | workshops werent relevant | Workshops not rel | 1
|  |  |  | where was MIT and SDSU faculty? | Strategic Vision | 1
IP discussion
strategic vision since I'm already familiar with csne
|  |  |  | Improvement (Raw Data) | Improvement | count
|  |  |  | Members should get slides to you sooner | IAB winged it | 1
|  |  |  | well run day, organized and purposeful | Get faculty / ldrs to dinner | 2
|  |  |  | Include the other schools or elimnate | Poster Printing | 1
|  |  |  | raj chet joel sam not at dinner | Tech Transfer deeper | 1
|  |  |  | don’t exclude MIT/SD, they should be there | More 1:1 interactions | 1
really very good day
Best Industry Day ever!
pick a better poster printer, posters printed poorly
tech transfer was good topic but the talk wasn't in-depth enough
get faculty to the student dinner
increased time for 1:1 interactions w IAB members
Hi Scott,
I didn't get to talk to you during the visit, but I meant to corner you and commend you for a really nice presentation. I am so impressed with the thoughtful and thorough approach you are taking.
Sorry I couldn't present on industry day. I hear it went really well. Hopefully next time.
-Eran

## Debrief Notes
Debrief Notes
General Suggestions
· Initiate engagement process with faculty earlier
· Proactively book/confirm travel for all attendees, especially International much earlier to save on Business class fares
· Work with Don to put in clauses for AV to protect MDT or book outside quality vendors
· Pre-book a speaker rehearsal dinner
· "Package" all of the presentations so they can be moved between PC's without loosing movies, sounds, images
· Follow CRDM model for car service for MDT employees and do a better job communicating to the employees. Better job notifying employees that there is a car waiting
o Determine in beginning if all attendees (including MDT) will receive ground transportation, this will help communicating in the beginning stages.
· For non-US visitors (customers and MDT attendees) confirm best way to manage if not using MDT US AMEX and group number
· Decide earlier (who is invited to cocktail party)
· Determine in beginning stages budget and who is responsible for what charges (field vs. marketing)
· For the site survey, determine how many adjacent concurrent meetings will be taking place that may cause traffic and NOISE problems outside the conf room.
· Create and assign on-site responsibilities earlier
· Consider Fri evening/Saturday program
· Consider less panel members - too many this go around
· Get the support teams involved sooner and be more proactive in overall sharing of responsibilities
What worked:
Faculty
· Rob Kowal did a great job as Co-Chair and should be used again in the future
· Dr Davies was engaging as Panel Moderator
· Great facility! The faculty were highly knowledgeable and represented multiple viewpoints.
· The panel discussions were very useful because they generated some good audience participation.
Overall
· Think the free time during lunch with posters etc.… was a great thing to have. Gave a time to meet, share, discuss and network.
· The weekly update calls and attendance downloads were very effective!
· 2 mikes on stands in audience worked WELL
· Notebooks pre-populated with Faculty names and agenda- not doing binders with full presentations was a good decision.
Venue
· Site provided adequate space for the size of group we had attend
· Setup and planning by planning team was extraordinary!
o Didn’t see anything missing that was supposed to be shipped and you all went with the flow as needs had to change due to various things.
o Everyone worked together and pitched in as needed to get things done.
· Welcome reception at the pool was an excellent networking opportunity for the attendees
· The location was beautiful and easily accessible
o Relaxing atmosphere
o Commute to the airport was good
o Food was good
For Improvement next time
Presentations
· There was some redundancy in the slides – probably because some of the presenters didn’t send their slides in a timely manner for review – It’s always a challenge with these meetings!
· Should have included all previous presenters in the panel discussions – I think in one or two cases one of the presenters wasn’t up there.
· There probably could have been even more practical, procedural content – More case studies for instance.
· More content related ARS questions needed
· Chairs / Moderators / Speakers need to wait longer for audience the chance to respond via ARS
· ARS background slide needs to be clean so as to visualize easier polling results
· Dr Davies could have been more responsive with planning prior to the meeting
· Didn’t receive some of the EU talks until Friday so little if any chance to review before presentation
· Make sure presentations don’t have patients names in any images/fluoros
· Got behind schedule and never recovered. Need to revisit total number of talks and allotted times. Allow 30-40 minutes versus 20 minutes.
o Needed to shorten the 3rd panel discussion for other items running long. Maybe build in 5min buffers into sessions through the day.
o Build in time for Q&A with talks (5min/talk)
Attendees
· As the CS team is supporting the bulk of the cases in the field, it would have been optimal to have them in attendance.
Overall
· On checklist – assigned who is printing boarding passes
· Wasn’t able to really enjoy the location because of
o So humid
o T&E meeting bunched in on Thursday
The Venue
· A/V issues (to put it lightly)
o Need better panel mikes
· Hotel Staff were very accommodating and helpful at first but lacking in follow up and responds time.
· Clearer instructions for the attendees as to where their luggage would be for departure on Friday
Questions to Address
· DD how do we want to communicate to the Faculty that should invoice there prep time? Did we keep track of any of the prep time?
· Did we get poster approval from the faculty to use these again?
· How do we all feel about the poster session --well received or never again?
· Evaluation results—I am compiling them and will give to DL and give the people that opted in names to Carol Juan, but do we need to do anything else with them? Do we need an Exec summary for the program?
· Did we like the online website to register?
· How do we feel the invitations printed and electronically worked, do we need to determine if we should do differently next time?
· When is the next time?